## PRINCIPIOS_OBJ
OCCUPATIONAL SAFETY AND HEALTH LINES AND OBJECTIVES
| GEB - Gerencia SST |  | Principles of OSH Management | Tactical OSH Plan
| 1 | Life Comes First for all our employees, as a Corporate Value
| 2 | NOBODY dies at work!
| 3 | All accidents can be prevented
| 4 | Safety and health require leadership
| 5 | Safety and health are profitable
| 6 | Work is a social determinant of health, and must not deteriorate our health; it must improve it.
| GEB - Gerencia SST |  | OSH Objectives | Tactical OSH Plan
OSH Strategic Objectives - GEB+SUBSIDIARIES
| 1 | MANAGE OPERATIONS SAFETY AT ALL OUR CONTROLLED SUBSIDIARIES TO ACHIEVE IN 2023 A RESULT OF THE LOST TIME INJURY FREQUENCY RATE INDICATOR* (LTIFR) OF 0.30 OR LOWER AND AN OSH PROACTIVE PERFORMANCE INDICATOR OF 90% OR HIGHER
| 2 | DESIGN AND IMPLEMENT THE COMPREHENSIVE WELL-BEING PLAN TO PROMOTE HEALTHY HABITS AND LIFESTYLES TO MAKE A POSITIVE CONTRIBUTION TO THE IMPROVEMENT OF THE QUALITY OF LIFE OF THE DIRECT EMPLOYEES OF GEB AND ENLAZA IN 2023
* Includes GEB Corporate and controlled subsidiaries: Enlaza, TGI, Calidda, Contugas, Electrodunas and Conecta.
Objectives of the Corporate OSH Process
| 1 | COMPLETE THE CULTURAL TRANSFORMATION PROJECT WITHIN THE TIME FRAMES DEFINED IN THE TIMETABLE AND ASSURE THE CLOSE-OUT OF THE CONTRACT (SPI) AT 90% OR HIGHER IN THE FIRST SEMESTER OF 2023
| 2 | INCREASE THE PERCEPTION OF THE DIRECT EMPLOYEES OF GEB + SUBSIDIARIES REGARDING THE MATURITY OF OCCUPATIONAL SAFETY AND HEALTH MANAGEMENT BY 3% IN 2023 (COMPARED TO THE 2022 RESULTS)
| 3 | COMPLY WITH THE TIMETABLE OF THE COMPREHENSIVE WELL-BEING PLAN COVERING GEB CORPORATE + ENLAZA, WITH AN SPI AT 90% OR HIGHER IN 2023
| 4 | IMPROVE ALIGNMENT WITH GEB'S CORPORATE OSH MANAGEMENT MODEL (INCLUDING GEB + SUBSIDIARIES), INCREASING BY AT LEAST 5% THE RESULT OBTAINED IN THE 2022 ASSESSMENT
| 5 | ADVANCE IN THE IMPLEMENTATION OF THE MANAGEMENT MODEL AT GEB+SUBSIDIARIES ACCORDING TO THE ESTABLISHED AND APPROVED WORK PLAN WITH AN SPI OF 90% OR HIGHER IN 2023

## PRIORIZACION SST
PROJECT DEFINITION - DEPLOYMENT OF OSH OBJECTIVES
Strategic Perspective | Strategic OSH Objectives | OSH Process Objectives (Support) | Priority Projects | Project | Case for Action | Project Leader | When? |  | How? Key Actions | Inversión estimada | Measurement Indicators | Goal Indicators
[7 empty] | Start | End |  |  |  | 90% | 100% | 120%
Procesos | OBJECTIVE 1 MANAGE OPERATIONS SAFETY AT ALL OUR CONTROLLED SUBSIDIARIES TO ACHIEVE IN 2023 A RESULT OF THE LOST TIME INJURY FREQUENCY RATE INDICATOR* (LTIFR) OF 0.30 OR LOWER AND AN OSH PROACTIVE PERFORMANCE INDICATOR OF 90% OR HIGHER | COMPLETE THE CULTURAL TRANSFORMATION PROJECT WITHIN THE TIME FRAMES DEFINED IN THE TIMETABLE AND ASSURE THE CLOSE-OUT OF THE CONTRACT (SPI) AT 90% OR HIGHER IN THE FIRST SEMESTER OF 2023 | P1 | OSH CULTURAL TRANSFORMATION PROJECT Strengthen the Occupational Safety and Health Culture | Successfully complete the Culture Transformation Project following the guidelines of the Contracting Manual. | IPuentes ECala | 2023-01-01 | 2023-06-30 | Phase 3: Maintenance and continuous improvement of the Occupational Safety and Health Management System - Monitor the road map at each subsidiary and propose improvement initiatives depending on progress. - Field assistance and knowledge transfer. - Measure and monitor KPIs SETTLEMENT AND CLOSE-OUT OF THE CONTRACT Comply with the provisions of the Contracting Manual, performing the financial closing and formal settlement of the project, ensuring the traceability of the information (in accordance with document management guidelines). |  | Complete the scheduled Phase of Maintenance and Improvement, Settlement and Close-out (SPI) | SPI>= 87.5% | SPI>= 90% | SPI>= 95%
Processes | OBJECTIVE 1 MANAGE OPERATIONS SAFETY AT ALL OUR CONTROLLED SUBSIDIARIES TO ACHIEVE IN 2023 A RESULT OF THE LOST TIME INJURY FREQUENCY RATE INDICATOR* (LTIFR) OF 0.30 OR LOWER AND AN OSH PROACTIVE PERFORMANCE INDICATOR OF 90% OR HIGHER | IMPROVE ALIGNMENT WITH GEB'S CORPORATE OSH MANAGEMENT MODEL (INCLUDING GEB + SUBSIDIARIES), INCREASING BY AT LEAST 5% THE RESULT OBTAINED IN THE 2022 ASSESSMENT | P2 | OSH CULTURE STRENGTHENING PLAN Continue to consolidate the OSH Culture strengthening progress, make progress in closing gaps at each subsidiary in a manner that contributes to improving the perceived OSH Culture Maturity Level. | The focus of this process will be to "increase the level of maturity in safety” by incorporating behaviors, skills and tools that lead GEB towards a strong culture (generative) that leverages Operational Excellence. | IPuentes CVallejo | 2023-01-01 | 2023-12-31 | Deploy, assist and assess the practices of the Occupational Safety and Health Management model: 1. Leadership and Commitment 2. OSH Risk Assessment 3. Objectives, Goals and Programs 4. OSH Training and Learning 5. Legal Compliance, Documentation, Participation and Consultation 6. Contractor Management in OSH 7. Operational Risk Management, PSM and ESS 8. Emergency Management 9. Conformity verification - OSH Indicators 10. Deviation Treatment - Incidents / Accidents 11. OSH Governance and Critical Analysis Continue with the OSH Communications Plan in coordination with the Corporate Communications Plan, with support from an external specialist firm. Develop the message and strategy, and implement and improve its impact. |  | - Lost Time Injury Frequency Rate (LTIFR) - Result of OSH Management Model (RASST) Assessment - OSH Management Maturity Level Perception Index (direct employees) (IPNMSST, for the Spanish original) - OSH Proactive Performance Indicator (PPI) | LTIFR <= 0.37 RASST >= 75% | LTIFR <= 0.30 RASST >= 78% | LTIFR <= 0.24 RASST >= 80%
|  | INCREASE THE PERCEPTION OF THE DIRECT EMPLOYEES OF GEB + SUBSIDIARIES REGARDING THE MATURITY OF OCCUPATIONAL SAFETY AND HEALTH MANAGEMENT BY 5% IN 2023 (COMPARED TO THE 2022 RESULTS) | [9 empty] | IPNMSST>=65% IDP>= 85% | IPNMSST>=68% IDP>= 90% | IPNMSST>=70% IDP>= 96%
Procesos | OBJECTIVE 1 MANAGE OPERATIONS SAFETY AT ALL OUR CONTROLLED SUBSIDIARIES TO ACHIEVE IN 2023 A RESULT OF THE LOST TIME INJURY FREQUENCY RATE INDICATOR* (LTIFR) OF 0.30 OR LOWER AND AN OSH PROACTIVE PERFORMANCE INDICATOR OF 90% OR HIGHER | ADVANCE IN THE IMPLEMENTATION OF THE MANAGEMENT MODEL AT GEB+SUBSIDIARIES ACCORDING TO THE ESTABLISHED AND APPROVED WORK PLAN WITH AN SPI OF 90% OR HIGHER IN 2023 | P3 | PROCESS SAFETY STRATEGIC PLAN Deploy the guidelines to systematically manage the Major Risks at each GEB subsidiary | Continue to develop the Process Safety Model to ensure efficient and timely management of the identification, assessment and management of major risks at each subsidiary. | IPuentes NCuervo | 2023-01-01 | 2023-12-31 | 1. Perform a gap analysis at GEB companies (baseline) and establish one (1) strategic action plan for GEB based on the results of the gap analysis in the first semester of 2023. 2. Define three (3) relevant and top priority process safety elements for process safety management at the GEB subsidiaries and develop corporate guidelines to manage them. (Procedure and performance indicators) 3. Design and agree with the subsidiaries and begin to report two (2) safety process reaction indicators each month (tier 1 and tier 2). 4. Review the corporate risk assessment matrix to verify its applicability to operating risk assessment and propose appropriate adjustments in the corresponding area to update the assessment, and assist in the review of the risk assessment matrices of the GEB subsidiaries. 5. . Manage the GEB process safety culture and leadership through the dissemination of the developed procedures and guidelines, 5 fliers during the year on relevant PS topics. |  | Compliance with the PSM(SPI- PSM) timetable | - SPI PSM>= 85% | - SPI PSM>= 90% | - SPI PSM>= 95%
Procesos | OBJECTIVE 2 DESIGN AND IMPLEMENT THE COMPREHENSIVE WELL-BEING PLAN TO PROMOTE HEALTHY HABITS AND LIFESTYLES TO MAKE A POSITIVE CONTRIBUTION TO THE IMPROVEMENT OF THE QUALITY OF LIFE OF THE DIRECT EMPLOYEES OF GEB AND ENLAZA IN 2023 | COMPLY WITH THE TIMETABLE OF THE COMPREHENSIVE WELL-BEING PLAN COVERING GEB CORPORATE + ENLAZA, WITH AN SPI AT 90% OR HIGHER IN 2023 | P4 | IMPLEMENTATION OF THE COMPREHENSIVE WELL-BEING PLAN Make progress in the development of the Comprehensive Well-being Plan to make a positive contribution on the improvement of the quality of life of our direct employees, incorporating tools that facilitate broader coverage and participation. | Improve people’s COMPREHENSIVE occupational health under the premise that a work environment must facilitate preserving, not deteriorating, health. | IPuentes Ecala MOtalora | 2023-01-01 | 2023-12-31 | 1. Update the baseline of risk factors. 2. Partnerships for insurance / Tools that drive action. 3. Creating a communication strategy to promote healthy habits and lifestyles. 4. Developing conducive environments to practice healthy habits. 5. Strengthening the program to promote healthy habits and lifestyles at work, carrying out periodic impact evaluations. |  | Complying with the Comprehensive Well-being Plan’s Schedule. | - Comprehensive Well-being Plan SPI > = 85% | - Comprehensive Well-being Plan SPI > = 90% | - Comprehensive Well-being Plan SPI > = 95%
Perspectiva Estratégica | Foco Estratégico
Financiera | Conexiones_de_Progreso
Mercados_Negocios | Transformacion_Territorios
Procesos | Promocion_Agenda_Regulatoria
Innovación_Crecimiento_Aprendizaje | Resiliencia_climatica
Hub_Colaboracion_Energías_Eficientes
Transformacion_Cultural_SST
OBJECTIVE 1 MANAGE OPERATIONS SAFETY AT ALL OUR CONTROLLED SUBSIDIARIES TO ACHIEVE IN 2023 A RESULT OF THE LOST TIME INJURY FREQUENCY RATE INDICATOR* (LTIFR) OF 0.30 OR LOWER AND AN OSH PROACTIVE PERFORMANCE INDICATOR OF 90% OR HIGHER
OBJECTIVE 2 DESIGN AND IMPLEMENT THE COMPREHENSIVE WELL-BEING PLAN TO PROMOTE HEALTHY HABITS AND LIFESTYLES TO MAKE A POSITIVE CONTRIBUTION TO THE COMPREHENSIVE WELL-BEING OF THE DIRECT EMPLOYEES OF GEB AND ENLAZA IN 2023
OBJECTIVE 1 + OBJECTIVE 2

## PLAN_ACCION_SST
TALENT MANAGEMENT DEPARTMENT / OCCUPATIONAL SAFETY AND HEALTH OFFICE | [7 empty] | WEEKLY MONITORING - GANTT | [20 empty] | ANNUAL OCCUPATIONAL SAFETY AND HEALTH PLAN
Current Week | [6 empty] | 53 |  |  | Degree of Progress | [11 empty] | █
Phases/ Activity | Líder de Práctica | Weeks |  |  | % Progress | Monitoring - Month / Weeks
|  | Start | End | Duration |  |  | 2023-01-01 |  |  |  |  | 2023-02-01 |  |  |  | 2023-03-01 |  |  |  | 2023-04-01 |  |  |  | 2023-05-01 |  |  |  |  | 2023-06-01 |  |  |  | 2023-07-01 |  |  |  |  | 2023-08-01 |  |  |  | 2023-09-01 |  |  |  | 2023-10-01 |  |  |  |  | 2023-11-01 |  |  |  | 2023-12-01
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
P1. OSH Culture Transformation Project | ECala | 1 | 37 | 36 | 99% | bar: 2023-01-01 1 to 2023-09-01 36
MAINTENANCE AND CONTINOUS IMPROVEMENT | ECala | 1 | 10 | 9 | 100% | bar: 2023-01-01 1 to 2023-02-01 9
Review deviations and establish improvement plan | ECala | 1 | 10 | 9 | 100% | [54 empty] | 0 | bar: 2023-01-01 1 to 2023-02-01 9
Review of results by senior management | ECala | 1 | 10 | 9 | 100% | bar: 2023-01-01 1 to 2023-02-01 9
KPI MEASUREMENT AND MONITORING | ECala | 1 | 10 | 9 | 100% | bar: 2023-01-01 1 to 2023-02-01 9
Review and monitor the project’s dashboard | ECala | 1 | 10 | 9 | 100% | bar: 2023-01-01 1 to 2023-02-01 9
Review and monitor the KPIs of the OSH management system | ECala | 1 | 10 | 9 | 100% | bar: 2023-01-01 1 to 2023-02-01 9
FIELD ASSISTANCE AND KNOWLEDGE TRANSFER | ECala | 1 | 10 | 9 | 100% | bar: 2023-01-01 1 to 2023-02-01 9
Implementation of Train the Trainer | ECala | 1 | 10 | 9 | 100% | bar: 2023-01-01 1 to 2023-02-01 9
Assess the performance of multipliers | ECala | 1 | 10 | 9 | 100% | bar: 2023-01-01 1 to 2023-02-01 9
Assess the performance of the committees | ECala | 1 | 10 | 9 | 100% | bar: 2023-01-01 1 to 2023-02-01 9
COMPLETE PMO PROJECT AND SETTLE CONTRACT AND ITS CONTRACTUAL PHASES | ECala | 7 | 37 | 30 | 96% | bar: 2023-02-01 7 to 2023-08-01 35
Update policies for contract amendments | ECala | 10 | 12 | 2 | 100% | bar: 2023-03-01 10 to 2023-03-01 11
Review deliverables by phase | ECala | 7 | 13 | 6 | 100% | bar: 2023-02-01 7 to 2023-03-01 12
Perform pending dissemination activities | ECala | 14 | 18 | 4 | 100% | bar: 2023-04-01 14 to 2023-04-01 17
Pay last invoice | ECala | 19 | 21 | 2 | 100% | bar: 2023-05-01 19 to 2023-05-01 20
Request account status for settlement | ECala | 22 | 23 | 1 | 100% | bar: 2023-05-01 22
Review of deliverables by sourcing legal area | ECala | 24 | 28 | 4 | 100% | bar: 2023-06-01 24 to 2023-07-01 27
Issue contractor experience certificate | ECala | 29 | 30 | 1 | 100% | bar: 2023-07-01 29
Issue final reception certificate | ECala | 31 | 32 | 1 | 80% | bar: 2023-07-01 31
Settlement certificate | ECala | 33 | 36 | 3 | 80% | bar: 2023-08-01 33 to 2023-08-01 35
Documentation of close-out of PMO project | ECala | 12 | 37 | 25 | 100% | bar: 2023-03-01 12 to 2023-09-01 36
Organizational Change Management | ECamelo | 1 | 54 | 53 | 95.12% | bar: 2023-01-01 1 to 2023-12-01 51
Sponsorship Coalition | ECamelo | 6 | 14 | 8 | 100% | bar: 2023-02-01 6 to 2023-03-01 13
Disseminate the Change Plan with the Project Sponsor | ECamelo | 6 | 6 | 2 | 100% | bar: 2023-02-01 6 to 2023-02-01 7
Submit project status to Administrative and TH VP | ECamelo | 7 | 7 | 1 | 100% | bar: 2023-02-01 7
Establish schedule of meetings at Corporate and Subsidiaries to activate the coalition | ECamelo | 6 | 12 | 6 | 100% | bar: 2023-02-01 6 to 2023-03-01 11
Consolidate the ANS with the Synergies Center for the effects of Training and Orientation | ECamelo | 12 | 14 | 2 | 100% | bar: 2023-03-01 12 to 2023-03-01 13
Transfer of Ownership | ECamelo | 9 | 17 | 8 | 100% | bar: 2023-02-01 9 to 2023-04-01 16
Hold focus group with the OSH teams at the subsidiaries (Resistance Management) | ECamelo | 11 | 14 | 4 | 100% | bar: 2023-03-01 11 to 2023-04-01 14
Coordinate the transfer of knowledge between the Corporate team, the Subsidiaries and the consultant. | ECamelo | 10 | 12 | 3 | 100% | bar: 2023-03-01 10 to 2023-03-01 12
Support the structure of the Multipliers Program | ECamelo | 9 | 14 | 5 | 100% | bar: 2023-02-01 9 to 2023-03-01 13
Assure preparation of the Trainers work plan | ECamelo | 16 | 17 | 2 | 100% | bar: 2023-04-01 16 to 2023-04-01 17
Maintenance Activities on the Change Plan | ECamelo | 15 | 32 | 17 | 100% | bar: 2023-04-01 15 to 2023-07-01 31
Assist in the field / observation visit | Ecamelo | 15 | 18 | 4 | 100% | bar: 2023-04-01 15 to 2023-05-01 18
Take Adkar survey | Ecamelo | 24 | 26 | 3 | 100% | bar: 2023-06-01 24 to 2023-06-01 26
Monitor project PCT | Ecamelo | 30 | 32 | 3 | 100% | bar: 2023-07-01 30 to 2023-08-01 32
Monitor the defined diagnosis, change strategy and sponsorship map | Ecamelo | 28 | 31 | 4 | 100% | bar: 2023-07-01 28 to 2023-07-01 31
OSHMS - Practice 1. Leadership and Commitment | IPuentes | 1 | 46 | 45 | 100% | bar: 2023-01-01 1 to 2023-11-01 45
Review / Update Commitment to Occupational Safety and Health | IPuentes | 14 | 17 | 3 | 100% | bar: 2023-04-01 14 to 2023-04-01 16
Annual ratification of the Commitment to Occupational Safety, Health and Well-being | IPuentes | 17 | 18 | 1 | 100%
Review and update the corporate IMS policy. Dissemination and communication | GProcesos | 1 | 5 | 4 | 100% | bar: 2023-01-01 1 to 2023-01-01 4
Strengthen proactive practices | CVallejo | 11 | 46 | 35 | 100% | bar: 2023-03-01 11 to 2023-11-01 45
Implement ODC training plan (strategic level corporate leaders) | CVallejo | 11 | 27 | 16 | 100% | bar: 2023-03-01 11 to 2023-06-01 26
Assist in implementation of ODC/ Management Visit (on-site) by Senior Management (strategic level) | CVallejo | 14 | 46 | 32 | 100% | bar: 2023-04-01 14 to 2023-11-01 45
OSHMS - Practice 2. OSH Risk Assessment | EVargas | 10 | 60 | 50 | 100% | bar: 2023-03-01 10 to 2023-12-01 53
Update Hazard Matrices by Process | EVargas | 10 | 15 | 5 | 100% | bar: 2023-03-01 10 to 2023-04-01 14
Unfold MIPVR GEB-UT in the corporate matrix and update according to the activity defined by GEB Corporate | EVargas | 10 | 15 | 5 | 100% | bar: 2023-03-01 10 to 2023-04-01 14
Monitor compliance with MIPVR controls (quarterly) | EVargas | 10 | 60 | 50 | 100% | bar: 2023-03-01 10 to 2023-12-01 53
Monitor compliance with MIPVR controls at GEB Corporate | EVargas | 10 | 60 | 50 | 100% | bar: 2023-03-01 10 to 2023-12-01 53
OSHMS - Practice 3. Objectives, goals, and programs | IPuentes | 1 | 54 | 53 | 90.24% | bar: 2023-01-01 1 to 2023-11-01 48
Develop/Approve proposal of OSH indicators and goals for CMI Corporate and Subsidiaries | IPuentes | 1 | 54 | 53 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Prepare OSH Annual Work Plan | IPuentes | 1 | 54 | 53 | 100%
Define targets for each proactive practice (corporate and subsidiary) | IPuentes | 6 | 10 | 4 | 100% | bar: 2023-02-01 6 to 2023-02-01 9
Define planning, performance, scope and quality criteria (corporate and subsidiary) | IPuentes | 6 | 10 | 4 | 100% | bar: 2023-02-01 6 to 2023-02-01 9
Detail the OSH annual action plan | IPuentes | 1 | 10 | 10 | 100% | bar: 2023-01-01 1 to 2023-03-01 10
Disseminate/Approve with GT department and COPASST | IPuentes | 8 | 10 | 5 | 100% | bar: 2023-02-01 8 to 2023-03-01 12
Signing of annual plan by the Registered Agent | IPuentes | 13 | 10 | 3 | 100% | bar: 2023-03-01 13 to 2023-04-01 15
Implementation of the AON wellbeing ecosystem | ECala | 11 | 53 | 42 | 60% | bar: 2023-03-01 11 to 2023-09-01 36
Implementation of the AON wellbeing program | ECala | 11 | 48 | 37 | 40% | bar: 2023-03-01 11 to 2023-06-01 25
Sign AON contract | ECala | 11 | 16 | 5 | 100% | bar: 2023-03-01 11 to 2023-04-01 15
Gather information to deliver to AON | ECala | 16 | 18 | 2 | 100% | bar: 2023-04-01 16 to 2023-04-01 17
Take survey of GEB OSH and well-being leaders | ECala | 18 | 19 | 1 | 100% | bar: 2023-05-01 18
Take survey of resilience for employees | ECala | 19 | 23 | 4 | 20% | bar: 2023-05-01 19
Multivariate analysis of the information | ECala | 23 | 27 | 4 | 0%
Delivery of results and recommendations for work plan | ECala | 29 | 31 | 2 | 0%
Documented handbook for 2023 | ECala | 32 | 40 | 8 | 0%
Site wellbeing | ECala | 40 | 48 | 8 | 0%
Application of AON WELLone | ECala | 18 | 53 | 35 | 80% | bar: 2023-05-01 18 to 2023-11-01 45
Test users | ECala | 18 | 22 | 4 | 100% | bar: 2023-05-01 18 to 2023-05-01 21
Expectations campaign | ECala | 22 | 30 | 8 | 100% | bar: 2023-05-01 22 to 2023-07-01 29
Create users and passwords | ECala | 31 | 33 | 2 | 100% | bar: 2023-07-01 31 to 2023-08-01 32
Start up with well-being challenge | ECala | 33 | 53 | 20 | 50% | bar: 2023-08-01 33 to 2023-10-01 42
Monitor usability metrics | ECala | 49 | 51 | 2 | 50% | bar: 2023-12-01 49
Update SVE DME (Vitality) | ECala | 4 | 54 | 50 | 100% | bar: 2023-01-01 4 to 2023-12-01 53
Generate the baseline of risk factors through the physical and emotional health survey (includes DME) | ECala | 16 | 24 | 8 | 100% | bar: 2023-04-01 16 to 2023-06-01 23
Classify employees to establish priorities (demographic description, absenteeism, periodic exams, surveys) | ECala | 16 | 19 | 3 | 100% | bar: 2023-04-01 16 to 2023-05-01 18
Identification of employee areas or groups with top priority for intervention according to the survey | ECala | 14 | 16 | 2 | 100% | bar: 2023-04-01 14 to 2023-04-01 15
Intervention in work conditions (work station inspections, 170 corporate and 80 branch in 2023) | ECala | 4 | 52 | 48 | 100% | bar: 2023-01-01 4 to 2023-12-01 51
Intervention on behaviors (DME prevention schools) | ECala | 18 | 34 | 16 | 100% | bar: 2023-05-01 18 to 2023-08-01 33
Monitor health conditions reports and AT/ forward cases to EPS | ECala | 4 | 52 | 48 | 100% | bar: 2023-01-01 4 to 2023-12-01 51
Follow up on actions or recommendations according to the IPT | ECala | 13 | 52 | 39 | 100% | bar: 2023-03-01 13 to 2023-12-01 51
Monthly monitoring of the program’s indicators | ECala | 6 | 54 | 48 | 100% | bar: 2023-02-01 6 to 2023-12-01 53
Posture health training (on site memory center) | ECala | 22 | 27 | 5 | 100% | bar: 2023-05-01 22 to 2023-06-01 26
Virtual posture health training (all employees) | ECala | 26 | 30 | 4 | 100% | bar: 2023-06-01 26 to 2023-07-01 29
Assess the Epidemiological Surveillance System according to the year’s results | ECala | 49 | 54 | 5 | 100% | bar: 2023-12-01 49 to 2023-12-01 53
Update Psycho-social Risk SVE (Vivamente) | ECala | 1 | 52 | 51 | 91.8% | bar: 2023-01-01 1 to 2023-11-01 47
Psycho-emotional assistance and orientation program, reported cases, high and very high risk | ECala | 6 | 52 | 46 | 100% | bar: 2023-02-01 6 to 2023-12-01 51
Disseminate program for detection and action of the emotional assistance and orientation program for Copasst and new Employee Relations Committee | ECala | 20 | 32 | 12 | 100% | bar: 2023-05-01 20 to 2023-07-01 31
Disseminate protocol for detection and action of the emotional assistance and orientation program to the Equality Committee | ECala | 23 | 33 | 10 | 100% | bar: 2023-06-01 23 to 2023-08-01 32
Promote psychological assistance for leaders program | ECala | 21 | 41 | 20 | 17% | bar: 2023-05-01 21 to 2023-06-01 24
Technostress and disconnect from work (new remote workers) | ECala | 16 | 22 | 6 | 100% | bar: 2023-04-01 16 to 2023-05-01 21
Self-awareness and self-regulation memory center | ECala | 10 | 12 | 2 | 100% | bar: 2023-03-01 10 to 2023-03-01 11
Sleep health Control Center 2 groups | ECala | 23 | 27 | 4 | 100% | bar: 2023-06-01 23 to 2023-06-01 26
Mental health conference (positive thinking culture) (Medplus) | ECala | 14 | 16 | 2 | 100% | bar: 2023-04-01 14 to 2023-04-01 15
Prevention of the Consumption of Alcohol, Tobacco and PAS | ECala | 20 | 22 | 2 | 100% | bar: 2023-05-01 20 to 2023-05-01 21
Structure and formalize contract to perform psycho-socio risk battery test | ECala | 1 | 13 | 12 | 100% | bar: 2023-01-01 1 to 2023-03-01 12
Application of psycho-social risk battery test 2022 (update risk groups) | ECala | 20 | 32 | 12 | 100% | bar: 2023-05-01 20 to 2023-07-01 31
Delivery of test results | ECala | 32 | 35 | 3 | 100% | bar: 2023-08-01 32 to 2023-08-01 34
Disseminate the results of the psycho-social risks survey by area | ECala | 37 | 49 | 12 | 60% | bar: 2023-09-01 37 to 2023-10-01 44
Structure work plan for risk intervention | ECala | 49 | 51 | 2 | 100% | bar: 2023-12-01 49 to 2023-12-01 50
Monitor indicators | ECala | 7 | 50 | 43 | 100% | bar: 2023-02-01 7 to 2023-12-01 49
Health Promotion and Prevention Material | ECala | 5 | 51 | 46 | 88.89% | bar: 2023-01-01 5 to 2023-11-01 45
World cancer day | ECala | 5 | 9 | 4 | 100% | bar: 2023-01-01 5 to 2023-02-01 8
World sleep day | ECala | 11 | 15 | 4 | 100% | bar: 2023-03-01 11 to 2023-04-01 14
World tuberculosis day | ECala | 11 | 15 | 4 | 100% | bar: 2023-03-01 11 to 2023-04-01 14
Prevention of acute respiratory infection | ECala | 11 | 15 | 4 | 100% | bar: 2023-03-01 11 to 2023-04-01 14
Vector-transmitted diseases (quarterly bulletin) | ECala | 18 | 22 | 4 | 100% | bar: 2023-05-01 18 to 2023-05-01 21
World hypertension day | ECala | 12 | 16 | 4 | 100% | bar: 2023-03-01 12 to 2023-04-01 15
Bee and wasp bites | ECala | 28 | 32 | 4 | 100% | bar: 2023-07-01 28 to 2023-07-01 31
World prostate cancer prevention day | ECala | 25 | 29 | 4 | 100% | bar: 2023-06-01 25 to 2023-07-01 28
World blood donor day | ECala | 26 | 30 | 4 | 100% | bar: 2023-06-01 26 to 2023-07-01 29
World breastfeeding day | ECala | 30 | 34 | 4 | 100% | bar: 2023-07-01 30 to 2023-08-01 33
World rabies and rabies accident prevention day | ECala | 35 | 39 | 4 | 100% | bar: 2023-08-01 35 to 2023-09-01 38
World heart day | ECala | 36 | 38 | 2 | 0%
World breast cancer day | ECala | 40 | 42 | 2 | 100% | bar: 2023-10-01 40 to 2023-10-01 41
World diabetes prevention day | ECala | 45 | 49 | 4 | 0%
World mental health day | ECala | 41 | 45 | 4 | 100% | bar: 2023-10-01 41 to 2023-10-01 44
Food-transmitted diseases (vacations) | ECala | 46 | 50 | 4 | 100% | bar: 2023-11-01 46 to 2023-12-01 49
Semi-annual public health assessment report 1 | ECala | 27 | 29 | 2 | 100% | bar: 2023-07-01 27 to 2023-07-01 28
Semi-annual public health assessment report 2 | ECala | 49 | 51 | 2 | 100% | bar: 2023-12-01 49 to 2023-12-01 50
Reincorporation to Work Program | ECala | 8 | 54 | 46 | 100% | bar: 2023-02-01 8 to 2023-12-01 53
Categorization and follow-up on those with medical recommendation / restrictions | ECala | 8 | 52 | 44 | 100% | bar: 2023-02-01 8 to 2023-12-01 51
Monitor the IPT generated by the reincorporation programs | ECala | 9 | 54 | 45 | 100% | bar: 2023-02-01 9 to 2023-12-01 53
Worker absenteeism program | ECala | 14 | 54 | 40 | 100% | bar: 2023-04-01 14 to 2023-12-01 53
Analysis and action plan on absenteeism indicators of the previous year | ECala | 32 | 54 | 22 | 100% | bar: 2023-08-01 32 to 2023-12-01 53
Monthly task group meeting with ARL to handle medical cases | ECala | 14 | 51 | 37 | 100% | bar: 2023-04-01 14 to 2023-12-01 50
Promotion and Prevention Activities | ECala | 14 | 42 | 28 | 71.43% | bar: 2023-04-01 14 to 2023-08-01 33
Prevention of breast cancer, VPH and cervical cancer ( virtual) | ECala | 14 | 22 | 8 | 100% | bar: 2023-04-01 14 to 2023-05-01 21
Prevention of prostate cancer (Medplus) | ECala | 26 | 30 | 4 | 100% | bar: 2023-06-01 26 to 2023-07-01 29
Blood donation program (district blood center) | ECala | 27 | 31 | 4 | 100% | bar: 2023-07-01 27 to 2023-07-01 30
Conference on a healthy heart culture (Medplus) | ECala | 14 | 18 | 4 | 0%
Adjustment to the preventive and occupational medicine procedure | ECala | 14 | 22 | 8 | 100% | bar: 2023-04-01 14 to 2023-05-01 21
Prevention of cardiovascular diseases | ECala | 32 | 36 | 4 | 0%
Conference on skin cancer and care tips | ECala | 38 | 42 | 4 | 100% | bar: 2023-09-01 38 to 2023-10-01 41
OSHMS - Practice 4. Training, Raising Awareness/Learning about OSH | CVallejo | 1 | 55 | 54 | 99.74% | bar: 2023-01-01 1 to 2023-12-01 53
Develop personnel OSH competencies | CVallejo | 1 | 55 | 54 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Produce monthly report on training plan (direct- third parties) | CVallejo | 1 | 55 | 54 | 100% | b | bar: 2023-01-01 1 to 2023-12-01 53
Analyzing the monitoring and report on results | CVallejo | 1 | 54 | 54 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Prepare detailed OSH training program Update OSH training matrix | CVallejo | 10 | 18 | 8 | 100% | bar: 2023-03-01 10 to 2023-04-01 17
OSH Orientation | CVallejo | 1 | 55 | 54 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Define audience for general orientation (direct new employees and contractors) and implement the assessment and certification program | CVallejo | 1 | 55 | 54 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Define audience for general retraining and implement the assessment and certification program | CVallejo | 1 | 54 | 54 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Implement OSH orientation for all levels and contractors | EVargas | 1 | 55 | 54 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Performance Management | CVallejo | 30 | 34 | 4 | 100% | bar: 2023-07-01 30 to 2023-08-01 33
Apply the performance assessment tool to Strategic and Tactical levels (Pilot plan, corporate and subsidiary) | CVallejo | 30 | 34 | 4 | 100% | bar: 2023-07-01 30 to 2023-08-01 33
Perform Proactive Observation of Behaviors Practice | CVallejo | 14 | 50 | 36 | 100% | bar: 2023-04-01 14 to 2023-12-01 49
Application of ODC by the assigned corporate leaders | CVallejo | 14 | 50 | 36 | 100% | bar: 2023-04-01 14 to 2023-12-01 49
Record ODC in the Prevsis application | CVallejo | 14 | 50 | 36 | 100% | bar: 2023-04-01 14 to 2023-12-01 49
Consolidate data on ODC compliance in the Corporate Proactive Performance Dashboard | CVallejo | 14 | 50 | 36 | 100% | bar: 2023-04-01 14 to 2023-12-01 49
Consolidate the ODC in the database of GEB - Subsidiaries | CVallejo | 14 | 50 | 36 | 100% | bar: 2023-04-01 14 to 2023-12-01 49
Implementation of Fair Culture | CVallejo | 6 | 54 | 48 | 98.18% | bar: 2023-02-01 6 to 2023-12-01 53
Ensure availability of the Fair Culture procedure in the Management Systems of GEB -Subsidiaries | CVallejo | 6 | 18 | 12 | 100% | bar: 2023-02-01 6 to 2023-04-01 17
Implement training plan GEB - Subsidiaries | CVallejo | 6 | 18 | 12 | 100% | bar: 2023-02-01 6 to 2023-04-01 17
Review, adjust and define matrix of individual and collective recognition - corporate | CVallejo | 14 | 18 | 4 | 100% | bar: 2023-04-01 14 to 2023-04-01 17
Review, adjust and define decision tree (based on 2022 critical analysis) | CVallejo | 18 | 22 | 4 | 100% | bar: 2023-05-01 18 to 2023-05-01 21
Hold workshop on application of the decision tree | CVallejo | 22 | 32 | 10 | 80% | bar: 2023-05-01 22 to 2023-07-01 29
Establish internal / external communication plan for recognition. | CVallejo | 18 | 32 | 14 | 100% | bar: 2023-05-01 18 to 2023-07-01 31
Apply recognition matrix and individual and collective awards at GEB | CVallejo | 32 | 54 | 22 | 100% | bar: 2023-08-01 32 to 2023-12-01 53
Apply matrix of criteria for penalties and decision tree at GEB | CVallejo | 32 | 54 | 22 | 100% | bar: 2023-08-01 32 to 2023-12-01 53
Measure results (indicator of recognition and penalties) | CVallejo | 32 | 54 | 22 | 100% | bar: 2023-08-01 32 to 2023-12-01 53
Dissemination through internal and external media | CVallejo | 32 | 54 | 22 | 100% | bar: 2023-08-01 32 to 2023-12-01 53
Perform critical analysis for maintenance and improvement based on the guidelines of Practice 11 | CVallejo | 47 | 50 | 3 | 100% | bar: 2023-11-01 47 to 2023-12-01 49
Lessons Learned | CVallejo | 10 | 54 | 44 | 100% | bar: 2023-03-01 10 to 2023-12-01 53
Develop repository of lessons learned | CVallejo | 10 | 54 | 44 | 100% | bar: 2023-03-01 10 to 2023-12-01 53
OSHMS - Practice 5. Legal compliance, Participation, Communication and Consultation | IPuentes | 1 | 57 | 56 | 88.18% | bar: 2023-01-01 1 to 2023-12-01 50
Create Copasst | EVargas | 1 | 12 | 11 | 100% | bar: 2023-01-01 1 to 2023-03-01 11
Bring to Copasst monthly topics related to the OSHMS | IPuentes | 3 | 57 | 54 | 100% | bar: 2023-01-01 3 to 2023-12-01 53
Training of Employee Relations Committee | EVargas | 11 | 31 | 20 | 100% | bar: 2023-03-01 11 to 2023-07-01 30
Update Industrial Hygiene and Safety Regulation | IPuentes | 14 | 22 | 8 | 100% | bar: 2023-04-01 14 to 2023-05-01 21
Update Matrix of OSH legal requirements (monthly) | EVargas | 3 | 53 | 50 | 100% | bar: 2023-01-01 3 to 2023-12-01 52
Assessment of compliance with legal requirements - Semester 1 | EVargas | 27 | 29 | 2 | 100% | bar: 2023-07-01 27 to 2023-07-01 28
Assessment of compliance with legal requirements - Semester 2 | EVargas | 48 | 50 | 2 | 0%
Disseminate policy on prevention of substance abuse | ECala | 22 | 28 | 6 | 100% | bar: 2023-05-01 22 to 2023-07-01 27
OSH Communication Plan | IPuentes | 10 | 54 | 44 | 100% | bar: 2023-03-01 10 to 2023-12-01 53
Take inventory of OSH communications needs, including Safety, Health and PSM | IPuentes | 10 | 12 | 2 | 100% | bar: 2023-03-01 10 to 2023-03-01 11
Coordinate 2023 strategy implementation with the Communications area | IPuentes | 12 | 14 | 2 | 100% | bar: 2023-03-01 12 to 2023-03-01 13
Define messages by audience, time line and areas: Vision Zero, Health and PSM | IPuentes | 14 | 16 | 2 | 100% | bar: 2023-04-01 14 to 2023-04-01 15
Develop contents - communications time line | IPuentes | 16 | 18 | 2 | 100% | bar: 2023-04-01 16 to 2023-04-01 17
Deploy 2023 Communications Strategy | IPuentes | 18 | 54 | 36 | 100% | bar: 2023-05-01 18 to 2023-12-01 53
Carry Out Proactive Reporting of Unsafe Conditions/Acts Practice | CVallejo | 1 | 55 | 54 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Evaluation and 2023 assessment and improvement plan | CVallejo | 14 | 20 | 6 | 100% | bar: 2023-04-01 14 to 2023-05-01 19
Ensure implementation of the Prevsis tool to record deviations | CVallejo | 1 | 25 | 24 | 100% | bar: 2023-01-01 1 to 2023-06-01 24
Provide OSH training to teams (direct and contractors) Tactical teams | CVallejo | 14 | 38 | 24 | 100% | bar: 2023-04-01 14 to 2023-09-01 37
Disseminate to all direct personnel and operations contractors | CVallejo | 14 | 22 | 8 | 100% | bar: 2023-04-01 14 to 2023-05-01 21
Record of monitoring of reports of acts and conditions and close cases | CVallejo | 15 | 39 | 24 | 100% | bar: 2023-04-01 15 to 2023-09-01 38
Consolidate the data in the dashboard (corporate and subsidiaries) | CVallejo | 1 | 55 | 54 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Consolidate the data of GEB corporate and subsidiaries (direct and contractors) in a unified database. | CVallejo | 17 | 54 | 37 | 100% | bar: 2023-04-01 17 to 2023-12-01 53
Hold critical analysis meetings for RdD based on the guidelines of Practice 11. | CVallejo | 23 | 54 | 31 | 100% | bar: 2023-06-01 23 to 2023-12-01 53
Evaluation and 2024 assessment and improvement plan | CVallejo | 36 | 40 | 4 | 100% | bar: 2023-09-01 36 to 2023-09-01 39
Develop multiplying mentors | CVallejo | 12 | 55 | 43 | 70% | bar: 2023-03-01 12 to 2023-10-01 42
Provide training to mentors (2023 cycle 2 - 2024 cycle 1) on the defined proactive practices | CVallejo | 12 | 23 | 11 | 60% | bar: 2023-03-01 12 to 2023-05-01 18
Assist in the field to apply proactive practices, virtually or on-site | CVallejo | 18 | 55 | 37 | 60% | bar: 2023-05-01 18 to 2023-10-01 40
Perform conformance verification: Compliance and quality of the practices performed and include the results in the dashboard | CVallejo | 18 | 55 | 37 | 60% | bar: 2023-05-01 18 to 2023-10-01 40
Hold the annual recognition event | CVallejo | 45 | 47 | 2 | 100% | bar: 2023-11-01 45 to 2023-11-01 46
OSHMS - Practice 6. Contractor Management | IPuentes | 1 | 55 | 54 | 83.33% | bar: 2023-01-01 1 to 2023-11-01 45
Intervention of prioritized partners and contractors | IPuentes | 10 | 54 | 44 | 100% | bar: 2023-03-01 10 to 2023-12-01 53
Establish a procedure to identify and assess OSH specifications in purchases and acquisitions of products and services. | IPuentes | 13 | 28 | 15 | 100% | bar: 2023-03-01 13 to 2023-07-01 27
Define the OSH aspects to be taken into consideration by the Company in the assessment and selection of providers and contractors. | IPuentes | 13 | 28 | 15 | 100% | bar: 2023-03-01 13 to 2023-07-01 27
Verify the priorities assigned to partners and contractors depending on their high potential for materialization of serious or fatal incidents. | IPuentes | 10 | 13 | 3 | 100% | bar: 2023-03-01 10 to 2023-03-01 12
Verify implementation of the documentation and field assessments in 2023 (on-site or virtual) for prioritized partners and contractors. | IPuentes | 10 | 13 | 3 | 100% | bar: 2023-03-01 10 to 2023-03-01 12
Strengthen leadership in the REMPAC by Sourcing / contract supervisors, verifying quality and compliance in performance | IPuentes | 14 | 30 | 16 | 100% | bar: 2023-04-01 14 to 2023-07-01 29
Verify definition in subsidiaries of bank of potential partners and contractors enabled in OSH (pre-contractual management) | IPuentes | 32 | 36 | 4 | 100% | bar: 2023-08-01 32 to 2023-08-01 35
Definition and implementation of the plan of recognition and warnings (post-contractual management) | IPuentes | 14 | 52 | 38 | 100% | bar: 2023-04-01 14 to 2023-12-01 51
Verify implementation and monitoring of the Contractor Alignment Plan (operations control) | IPuentes | 10 | 54 | 44 | 100% | bar: 2023-03-01 10 to 2023-12-01 53
Contractor Multipliers | CVallejo | 1 | 55 | 54 | 50% | bar: 2023-01-01 1 to 2023-07-01 27
Verify the selection of multipliers at the strategic and tactical levels of prioritized contractors | CVallejo | 14 | 18 | 4 | 100% | bar: 2023-04-01 14 to 2023-04-01 17
Verify performance of the proactive practices training plan | CVallejo | 18 | 31 | 13 | 100% | bar: 2023-05-01 18 to 2023-07-01 30
Verify the definition of targets for the application of proactive practices in the contractors’ dashboards | CVallejo | 18 | 22 | 4 | 100% | bar: 2023-05-01 18 to 2023-05-01 21
Verify the evaluation and monitoring in the contractor control dashboard | CVallejo | 18 | 53 | 35 | 0%
Verify definition and implementation of the contractor multiplier recognition plan | CVallejo | 21 | 25 | 4 | 0%
Assist in recognition for multipliers | CVallejo | 46 | 50 | 4 | 0%
Performance of Proactive Management Practice of Partners (REMPAC) | IPuentes | 1 | 55 | 54 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Central REMPAC meeting - Semester 1 | IPuentes | 29 | 30 | 1 | 100% | bar: 2023-07-01 29
Central REMPAC meeting - Semester 2 | IPuentes | 50 | 51 | 1 | 100% | bar: 2023-12-01 50
Consolidate data on REMPAC compliance in the Proactive Performance Dashboard | IPuentes | 1 | 55 | 54 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
OSHMS - Practice 7. Operational Risk Management - PGRC - ESS - P&P | CVallejo | 1 | 54 | 53 | 86.78% | bar: 2023-01-01 1 to 2023-11-01 46
PG Critical Risk Controls | CVallejo | 18 | 41 | 23 | 100% | bar: 2023-05-01 18 to 2023-10-01 40
Assist in the implementation of MORC Layout and Set-up at Enlaza and Conecta | CVallejo | 18 | 30 | 12 | 100% | bar: 2023-05-01 18 to 2023-07-01 29
Verify technical conformance of the PGRC Work at Heights at Subsidiaries | CVallejo | 18 | 22 | 4 | 100% | bar: 2023-05-01 18 to 2023-05-01 21
Verify technical conformance of the PGRC Excavation Work at Subsidiaries | CVallejo | 22 | 26 | 4 | 100% | bar: 2023-05-01 22 to 2023-06-01 25
Design Road Safety PGRC | CVallejo | 32 | 36 | 4 | 100% | bar: 2023-08-01 32 to 2023-08-01 35
Prepare checklists addressing the requirements to control critical equipment, machines and tools for the operation. | CVallejo | 32 | 36 | 4 | 100% | bar: 2023-08-01 32 to 2023-08-01 35
Call and coordinate meetings of the corporate task group | CVallejo | 37 | 41 | 4 | 100% | bar: 2023-09-01 37 to 2023-10-01 40
OSH field planning control | IPuentes | 14 | 51 | 37 | 34% | bar: 2023-04-01 14 to 2023-06-01 26
Include the Planning Control procedure in the field as a component of Practice 7. | IPuentes | 14 | 22 | 8 | 20% | bar: 2023-04-01 14 to 2023-04-01 15
Deliver training plan for pilot plan implementers | IPuentes | 22 | 28 | 6 | 10% | bar: 2023-05-01 22
Prepare and perform the practice implementation plan (pilot plan) | IPuentes | 22 | 46 | 24 | 40% | bar: 2023-05-01 22 to 2023-07-01 31
Validation adoption of the practice at the subsidiaries | IPuentes | 46 | 48 | 2 | 100% | bar: 2023-11-01 46 to 2023-11-01 47
Follow up on and close the improvement plan | IPuentes | 48 | 51 | 3 | 0%
Operational discipline | CVallejo | 1 | 54 | 53 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Carry out a OD training plan | CVallejo | 1 | 15 | 14 | 100% | bar: 2023-01-01 1 to 2023-04-01 14
Define targets by subsidiary for the Availability, Quality, Communication and Compliance phases | CVallejo | 14 | 18 | 4 | 100% | bar: 2023-04-01 14 to 2023-04-01 17
Plan and carry out activities to fulfill the defined goals | CVallejo | 18 | 44 | 26 | 100% | bar: 2023-05-01 18 to 2023-10-01 43
Monitor fulfillment of goals and ICS at corporate OSH meeting | CVallejo | 18 | 44 | 26 | 100% | bar: 2023-05-01 18 to 2023-10-01 43
Hold critical analysis meetings for DO based on the guidelines of Practice 11. | CVallejo | 22 | 48 | 26 | 100% | bar: 2023-05-01 22 to 2023-11-01 47
Incorporate the Operating Discipline documents in the program: Contractor Management Proactive practices, ASW, Fair Culture. Launch task groups | CVallejo | 18 | 20 | 2 | 100% | bar: 2023-05-01 18 to 2023-05-01 19
Occupational medicine assessments | ECala | 6 | 54 | 48 | 86.67% | bar: 2023-02-01 6 to 2023-11-01 47
Review diagnoses on health conditions | ECala | 8 | 10 | 2 | 100% | bar: 2023-02-01 8 to 2023-02-01 9
Update and review the professions chart | ECala | 7 | 8 | 1 | 100% | bar: 2023-02-01 7
Take occupational medical exams | ECala | 6 | 52 | 46 | 70% | bar: 2023-02-01 6 to 2023-09-01 38
Carry out executive check-ups | ECala | 6 | 54 | 48 | 90% | bar: 2023-02-01 6 to 2023-12-01 49
Follow up on occupational medicine recommendations | ECala | 6 | 54 | 48 | 80% | bar: 2023-02-01 6 to 2023-10-01 44
Monitor occupational medical examinations compliance indicator | ECala | 13 | 54 | 41 | 80% | bar: 2023-03-01 13 to 2023-11-01 45
Task groups (follow up on EL cases and critical EG cases) | ECala | 15 | 52 | 37 | 100% | bar: 2023-04-01 15 to 2023-12-01 51
Hold joint ARL-GEB task group meetings Quarter 1 | ECala | 15 | 16 | 1 | 100% | bar: 2023-04-01 15
Hold joint ARL-GEB task group meetings Quarter 2 | ECala | 28 | 29 | 1 | 100% | bar: 2023-07-01 28
Hold joint ARL-GEB task group meetings Quarter 3 | ECala | 41 | 42 | 1 | 100% | bar: 2023-10-01 41
Hold joint ARL-GEB task group meetings Quarter 4 | ECala | 51 | 52 | 1 | 100% | bar: 2023-12-01 51
Industrial Health Measurements | IPuentes | 23 | 27 | 4 | 100% | bar: 2023-06-01 23 to 2023-06-01 26
Breathing air quality measurements | IPuentes | 23 | 27 | 4 | 100% | bar: 2023-06-01 23 to 2023-06-01 26
Lighting measurements at administrative facilities, warehouses and memory center | IPuentes | 18 | 30 | 12 | 100% | bar: 2023-05-01 18 to 2023-07-01 29
OSHMS - Practice 8. Emergency Response Plan | EVargas | 10 | 42 | 32 | 62.5% | bar: 2023-03-01 10 to 2023-07-01 29
Prepare/Update Emergency Plans | EVargas | 10 | 12 | 2 | 100% | bar: 2023-03-01 10 to 2023-03-01 11
Update Master Emergency Plan | EVargas | 10 | 12 | 2 | 100% | bar: 2023-03-01 10 to 2023-03-01 11
Emergency Drills | EVargas | 22 | 42 | 20 | 100% | bar: 2023-05-01 22 to 2023-10-01 41
Emergency drills as administrative buildings (Calle 73, Pereira Office, Memory Center Office) | EVargas | 22 | 23 | 1 | 100% | bar: 2023-05-01 22
National evacuation drills at administrative buildings (Calle 73, Pereira Office, Memory Center Office) | EVargas | 41 | 42 | 1 | 100% | bar: 2023-10-01 41
Reconfigure emergency brigades of GEB /Mutual Support Agreements | EVargas | 14 | 36 | 22 | 0%
Establish and formalize mutual support agreements with Security personnel and SG at Calle 73 | EVargas | 14 | 16 | 2 | 0%
Train brigades and identify GEB brigade members (mutual support agreement personnel) | IPuentes | 16 | 22 | 6 | 0%
Training of GEB emergency brigades | EVargas | 27 | 36 | 9 | 50% | bar: 2023-07-01 27 to 2023-07-01 31
Training on save a life Bogotá (CPR) (Memory Center and Calle 73) | EVargas | 27 | 30 | 3 | 100% | bar: 2023-07-01 27 to 2023-07-01 29
CEO training and drill at GEB | IPuentes | 32 | 36 | 4 | 0%
OSHMS - Practice 9. Conformity Verification - OSH Indicators | IPuentes | 1 | 55 | 54 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Third-party audits of the OSHMS | IPuentes | 8 | 49 | 41 | 100% | bar: 2023-02-01 8 to 2023-11-01 48
Internal audit to follow up on ISO45001 certification (Icontec) | IPuentes | 8 | 11 | 3 | 100% | bar: 2023-02-01 8 to 2023-03-01 10
External audit to follow up on ISO45001 certification (BVQI) | IPuentes | 16 | 18 | 2 | 100% | bar: 2023-04-01 16 to 2023-04-01 17
Second-party OSH performance audit of contractors -ICONTEC | IPuentes | 23 | 49 | 26 | 100% | bar: 2023-06-01 23 to 2023-11-01 48
Assessment of OSH Model Alignment | CVallejo | 1 | 55 | 54 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Review and adjust assessment checklist | CVallejo | 27 | 30 | 3 | 100% | bar: 2023-07-01 27 to 2023-07-01 29
Perform Self Assessment with assessment of the OSH Model GEB - Subsidiaries | CVallejo | 32 | 36 | 4 | 100% | bar: 2023-08-01 32 to 2023-08-01 35
Perform assessment of OHS Model | CVallejo | 39 | 46 | 7 | 100% | bar: 2023-09-01 39 to 2023-11-01 45
Alignment of assessment action plan at Subsidiaries with corporate goal | CVallejo | 46 | 49 | 3 | 100% | bar: 2023-11-01 46 to 2023-11-01 48
Monitor compliance with the Assessment action plan - 2023 goal | CVallejo | 1 | 55 | 54 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Annual meeting for critical analysis and analysis of audit report | CVallejo | 46 | 52 | 6 | 100% | bar: 2023-11-01 46 to 2023-12-01 51
Consolidation of OSH Indicators | IPuentes | 6 | 54 | 48 | 100% | bar: 2023-02-01 6 to 2023-12-01 53
Consolidation of OSH Indicators | IPuentes | 6 | 54 | 48 | 100% | bar: 2023-02-01 6 to 2023-12-01 53
Monitor OSH ICS at OSH governance meetings | IPuentes | 7 | 54 | 47 | 100% | bar: 2023-02-01 7 to 2023-12-01 53
Tools for OSH Verification of Conformance | CVallejo | 1 | 54 | 53 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Verification of Quality and Compliance of the Practice tools: ODC, MORC, RQSV, REMPAC, RdD, CPLV, ATS, PT | CVallejo | 1 | 54 | 53 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Monitor Dashboard of Proactive Indicators (monthly) | CVallejo | 1 | 54 | 53 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
2023 OSH Culture Measurement | IPuentes | 24 | 49 | 25 | 100% | bar: 2023-06-01 24 to 2023-11-01 48
Define Culture Measurement implementation team | IPuentes | 24 | 26 | 2 | 100% | bar: 2023-06-01 24 to 2023-06-01 25
Adopt NOSACQ-50 methodology | IPuentes | 26 | 28 | 2 | 100% | bar: 2023-06-01 26 to 2023-07-01 27
Prepare 2023 culture measurement - Verification of the sample - Verification of operation of links - Start date, end date - Prepare launch with Human Resources and Communications team | IPuentes | 28 | 30 | 2 | 100% | bar: 2023-07-01 28 to 2023-07-01 29
Distribute survey to be filled out 2023 | IPuentes | 30 | 35 | 5 | 100% | bar: 2023-07-01 30 to 2023-08-01 34
Gather and analyze the 2023 data | IPuentes | 35 | 37 | 2 | 100% | bar: 2023-08-01 35 to 2023-09-01 36
Prepare and deliver the 2023 report | IPuentes | 37 | 40 | 3 | 100% | bar: 2023-09-01 37 to 2023-09-01 39
Disseminate and accept the 2023 report | IPuentes | 40 | 45 | 5 | 100% | bar: 2023-10-01 40 to 2023-10-01 44
Prepare 2024 maintenance and improvement action plan | IPuentes | 45 | 49 | 4 | 100% | bar: 2023-11-01 45 to 2023-11-01 48
OSHMS - Practice 10. Deviations Treatment - ATEL Investigation | CVallejo | 14 | 54 | 40 | 50% | bar: 2023-04-01 14 to 2023-08-01 33
Accident / Incident Investigation | CVallejo | 14 | 22 | 8 | 0%
Review and adjust the investigation report to address the requirements of the Fair Culture - Decision Tree | CVallejo | 14 | 22 | 8 | 0%
Authority to stop work | CVallejo | 14 | 54 | 40 | 100% | bar: 2023-04-01 14 to 2023-12-01 53
Verification of availability of the ASW procedure GEB - Subsidiaries | CVallejo | 14 | 16 | 2 | 100% | bar: 2023-04-01 14 to 2023-04-01 15
Draft action plan to implement, maintain and improve ASW GEB - Subsidiaries | CVallejo | 16 | 20 | 4 | 100% | bar: 2023-04-01 16 to 2023-05-01 19
Implement ASW action plan | CVallejo | 20 | 54 | 34 | 100% | bar: 2023-05-01 20 to 2023-12-01 53
Assess practical application | CVallejo | 45 | 49 | 4 | 100% | bar: 2023-11-01 45 to 2023-11-01 48
OSHMS - Practice 11. Governance and Critical Analysis | IPuentes | 1 | 55 | 54 | 87.78% | bar: 2023-01-01 1 to 2023-11-01 48
Operation of the corporate and subsidiary Life Comes First committees | IPuentes | 1 | 55 | 54 | 75.56% | bar: 2023-01-01 1 to 2023-10-01 41
Verify the technical and regulatory of the GEB CPLV procedure and guidelines | IPuentes | 14 | 16 | 2 | 100% | bar: 2023-04-01 14 to 2023-04-01 15
Raise awareness of the corporate Life Comes First Committee | IPuentes | 16 | 18 | 2 | 0%
Implement and put into operation corporate CPLV | IPuentes | 18 | 48 | 30 | 0%
Draft procedure on OSH governance meetings | IPuentes | 11 | 14 | 3 | 100% | bar: 2023-03-01 11 to 2023-03-01 13
Comply with meetings timetable (corporate / subsidiary) | IPuentes | 1 | 55 | 54 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Hold critical analysis meetings for CPLV (corporate/subsidiaries) based on the guidelines of Practice 11. | IPuentes | 18 | 48 | 30 | 100% | bar: 2023-05-01 18 to 2023-11-01 47
Define Practice leaders and OSH facilitators of the OSH model (corporate/subsidiary) | IPuentes | 18 | 22 | 4 | 100% | bar: 2023-05-01 18 to 2023-05-01 21
Implement specific training plan, for Practice leaders and OSH facilitators of the OSH model (corporate/subsidiary) | IPuentes | 22 | 28 | 6 | 80% | bar: 2023-05-01 22 to 2023-06-01 26
Assess quality and compliance of the practice committees | IPuentes | 18 | 48 | 30 | 100% | bar: 2023-05-01 18 to 2023-11-01 47
Follow-up on technical task groups | CVallejo | 1 | 55 | 54 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Define and structure task groups: Verification of availability and conformance of the OSH model on file. | CVallejo | 24 | 40 | 16 | 100% | bar: 2023-06-01 24 to 2023-09-01 39
Corporate task group meetings: Process Safety | CVallejo | 1 | 55 | 54 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Define and structure corporate task group: Field planning control | CVallejo | 14 | 22 | 8 | 100% | bar: 2023-04-01 14 to 2023-05-01 21
Corporate task group meetings: Critical risks: Key aspects: Management of critical risks to people, infrastructure, processes | CVallejo | 14 | 50 | 36 | 100% | bar: 2023-04-01 14 to 2023-12-01 49
Corporate task group meetings: Contractor Management: Key aspects: OSH Manual, standardization, recognitions/penalties. | CVallejo | 14 | 50 | 36 | 100% | bar: 2023-04-01 14 to 2023-12-01 49
External task group meetings: Contractor Management: Key aspects: OSH Manual (Isa Colombia - Enlaza) | CVallejo | 8 | 28 | 20 | 100% | bar: 2023-02-01 8 to 2023-07-01 27
Critical analysis for ODC, MORC | C. Vallejo | 18 | 50 | 32 | 100% | bar: 2023-05-01 18 to 2023-12-01 49
Manage the findings in ODC, MORC. | C. Vallejo | 18 | 50 | 32 | 100% | bar: 2023-05-01 18 to 2023-12-01 49
Monitor action plans arising from critical analysis | C. Vallejo | 18 | 50 | 32 | 100% | bar: 2023-05-01 18 to 2023-12-01 49
PROCESS SAFETY STRATEGIC PLAN (CORPOATE LEVEL) | NCuervo | 1 | 49 | 48 | 83.33% | bar: 2023-01-01 1 to 2023-10-01 40
Perform a gap analysis at GEB companies (baseline) and establish one (1) strategic action plan for GEB based on the results of the gap analysis in the first semester of 2023. | NCuervo | 6 | 27 | 21 | 100% | bar: 2023-02-01 6 to 2023-06-01 26
Prepare gap analysis methodology | NCuervo | 6 | 18 | 12 | 100% | bar: 2023-02-01 6 to 2023-04-01 17
Perform pilot gap analysis (Conecta and Calidda). | NCuervo | 10 | 18 | 8 | 100% | bar: 2023-03-01 10 to 2023-04-01 17
Analysis of the results of the gap analysis and adjust methodology. | NCuervo | 14 | 18 | 4 | 100% | bar: 2023-04-01 14 to 2023-04-01 17
Perform gap analysis at the Peruvian subsidiaries (Contugas, Electrodunas and Calidda). | NCuervo | 18 | 27 | 9 | 100% | bar: 2023-05-01 18 to 2023-06-01 26
Perform gap analysis at the Guatemalan subsidiary (Conecta). | NCuervo | 23 | 27 | 4 | 100% | bar: 2023-06-01 23 to 2023-06-01 26
Prepare report on GEB Gap Analysis. | NCuervo | 27 | 32 | 5 | 100% | bar: 2023-07-01 27 to 2023-07-01 31
Prepare strategic action plan to close gaps in process safety management. | NCuervo | 27 | 36 | 9 | 100% | bar: 2023-07-01 27 to 2023-08-01 35
Define two (2) relevant and top priority process safety elements for process safety management at the GEB subsidiaries and develop corporate guidelines to manage them. (Procedure and performance indicators) | NCuervo | 1 | 49 | 48 | 100% | bar: 2023-01-01 1 to 2023-11-01 48
Propose and approve the list of PS elements to be managed in 2023 (initial proposal "Identification of hazards and risk assessment" and "Incident Reporting and Investigation." | NCuervo | 1 | 10 | 9 | 100% | bar: 2023-01-01 1 to 2023-02-01 9
Review the process of identifying hazards and analyzing risks of each subsidiary's processes to ensure that operating risks are systematically evaluated. | NCuervo | 23 | 45 | 22 | 100% | bar: 2023-06-01 23 to 2023-10-01 44
Formulate performance indicator to monitor the closure and/or attention and/or implementation of measures for treating identified high and very high risks. | NCuervo | 27 | 40 | 13 | 100% | bar: 2023-07-01 27 to 2023-09-01 39
Review the reporting and investigation process of each subsidiary to ensure that incidents are reported and investigated in a timely, structured, and permanent manner. | NCuervo | 27 | 49 | 22 | 100% | bar: 2023-07-01 27 to 2023-11-01 48
Formulate a performance indicator to monitor the closure and/or attention and/or implementation of the activities for the closure of the action plans set out in the investigation reports of incidents. | NCuervo | 32 | 45 | 13 | 100% | bar: 2023-08-01 32 to 2023-10-01 44
Design and agree with the subsidiaries and begin to report two (2) safety process reaction indicators each month (tier 1 and tier 2). | NCuervo | 1 | 54 | 53 | 100% | bar: 2023-01-01 1 to 2023-12-01 53
Design the Process Safety incident indicators in Tier 1 and 2. | NCuervo | 1 | 10 | 9 | 100% | bar: 2023-01-01 1 to 2023-02-01 9
Agree with subsidiaries and begin to report monthly records on the 2 indicators (Tier 1 and 2). | NCuervo | 6 | 54 | 48 | 100% | bar: 2023-02-01 6 to 2023-12-01 53
Manage at the subsidiaries the implementation of the PS incident recording practice in the corporate tool (e.g. Prevsis) and the incorporation of the indicators in the corporate management dashboards so they can be viewed and monitored throughout GEB. | NCuervo | 6 | 23 | 17 | 100% | bar: 2023-02-01 6 to 2023-05-01 22
Monitor and assess trends | NCuervo | 10 | 54 | 44 | 100% | bar: 2023-03-01 10 to 2023-12-01 53
Submit proposal to include PS incidents in GEB’s strategic risk matrix. | NCuervo | 6 | 27 | 21 | 100% | bar: 2023-02-01 6 to 2023-06-01 26
Arrange meetings with the Strategic Planning Department to propose the revision of the corporate strategic risk matrix. | NCuervo | 6 | 18 | 12 | 100% | bar: 2023-02-01 6 to 2023-04-01 17
Submit proposal to include PS incidents in GEB’s strategic risk matrix to the Strategic Planning Department. | NCuervo | 6 | 14 | 8 | 100% | bar: 2023-02-01 6 to 2023-03-01 13
Follow up on the requirements and advancement in the adoption of the proposal by the Audit and Risk Committee and its communication to the subsidiaries. | NCuervo | 6 | 27 | 21 | 100% | bar: 2023-02-01 6 to 2023-06-01 26
Review the corporate risk assessment matrix to verify its applicability to operating risk assessment and propose appropriate adjustments in the corresponding area to update the assessment, and assist in the review of the risk assessment matrices of the GEB subsidiaries | NCuervo | 14 | 36 | 22 | 0%
Arrange meetings with the Strategic Planning Department to propose the revision of the corporate risk assessment matrix. | NCuervo | 14 | 36 | 22 | 0%
Submit to the Strategic Planning Department the appropriate adjustments to the corporate risk assessment, to ensure its applicability to the assessment of operating risks. | NCuervo | 23 | 32 | 9 | 0%
Review the risk assessment matrices of the GEB subsidiaries and arrange through the appropriate area the alignment of these matrices with the corporate matrix. | NCuervo | 27 | 36 | 9 | 0%
Manage the GEB process safety culture and leadership through the dissemination of the developed procedures and guidelines, 5 fliers during the year on relevant PS topics. | NCuervo | 10 | 54 | 44 | 100% | bar: 2023-03-01 10 to 2023-12-01 53
Disseminate fliers, knowledge pills, PS alerts. | NCuervo | 10 | 49 | 39 | 100% | bar: 2023-03-01 10 to 2023-11-01 48
Disseminate drafted and/or updated guidelines/ procedures/ indicator history, etc. (attach attendance lists). | NCuervo | 10 | 54 | 44 | 100% | bar: 2023-03-01 10 to 2023-12-01 53
ALIGNMENT OF OSH CRITERIA WITH TRANSMISSION CONTRACTORS ISA-GEB | Ipuentes | 8 | 28 | 20 | 100% | bar: 2023-02-01 8 to 2023-07-01 27
Meeting to define scope and work timetable | IPuentes | 8 | 9 | 1 | 100% | bar: 2023-02-01 8
Work Control / Work Permits | IPuentes | 9 | 11 | 2 | 100% | bar: 2023-02-01 9 to 2023-03-01 10
Validation by ISA-GEB technical teams | Lcoy | 11 | 13 | 2 | 100% | bar: 2023-03-01 11 to 2023-03-01 12
Operating Control OSH Requirements | IPuentes | 11 | 25 | 14 | 100% | bar: 2023-03-01 11 to 2023-06-01 24
TAR – Electrical risk | IPuentes | 11 | 13 | 2 | 100% | bar: 2023-03-01 11 to 2023-03-01 12
Validation by ISA-GEB technical teams | Lcoy | 13 | 15 | 2 | 100% | bar: 2023-03-01 13 to 2023-04-01 14
TAR – Work at Heights | IPuentes | 13 | 15 | 2 | 100% | bar: 2023-03-01 13 to 2023-04-01 14
Validation by ISA-GEB technical teams | Lcoy | 15 | 17 | 2 | 100% | bar: 2023-04-01 15 to 2023-04-01 16
TAR– Load lifting | IPuentes | 15 | 17 | 2 | 100% | bar: 2023-04-01 15 to 2023-04-01 16
Validation by ISA-GEB technical teams | Lcoy | 17 | 19 | 2 | 100% | bar: 2023-04-01 17 to 2023-05-01 18
TAR – Excavations | IPuentes | 17 | 19 | 2 | 100% | bar: 2023-04-01 17 to 2023-05-01 18
Validation by ISA-GEB technical teams | Lcoy | 19 | 21 | 2 | 100% | bar: 2023-05-01 19 to 2023-05-01 20
TAR – Confined spaces | IPuentes | 19 | 21 | 2 | 100% | bar: 2023-05-01 19 to 2023-05-01 20
Validation by ISA-GEB technical teams | Lcoy | 21 | 23 | 2 | 100% | bar: 2023-05-01 21 to 2023-05-01 22
TAR – Dangerous energies | IPuentes | 21 | 23 | 2 | 100% | bar: 2023-05-01 21 to 2023-05-01 22
Validation by ISA-GEB technical teams | Lcoy | 23 | 25 | 2 | 100% | bar: 2023-06-01 23 to 2023-06-01 24
TAR – Vehicle driving | IPuentes | 23 | 25 | 2 | 100% | bar: 2023-06-01 23 to 2023-06-01 24
Validation by ISA-GEB technical teams | Lcoy | 25 | 27 | 2 | 100% | bar: 2023-06-01 25 to 2023-06-01 26
OSH Requirements - Other critical activities | IPuentes | 25 | 26 | 1 | 100% | bar: 2023-06-01 25
Validation by ISA-GEB technical teams | Lcoy | 26 | 27 | 1 | 100% | bar: 2023-06-01 26
General Requirements | IPuentes | 26 | 27 | 1 | 100% | bar: 2023-06-01 26
Validation by ISA-GEB technical teams | Lcoy | 27 | 28 | 1 | 100% | bar: 2023-07-01 27
Specific OSH requirements | IPuentes | 27 | 28 | 1 | 100% | bar: 2023-07-01 27
Validation by ISA-GEB technical teams | Lcoy | 28 | 29 | 1 | 100% | bar: 2023-07-01 28
Practice leader
|  | Activities completed |  |  | 88.4%
|  | Activities in progress |  |  | 11.6%